## IBC Group_TS
Instruction: use a separate time sheet for each calendar month DO NOT TOUCH FORMULAS / Print on a front page in portrait mode / Automatic layout | [7 empty] | Enter below the weekend days that can not be worked
Friday
| IBC Group PLC | [6 empty] | Saturday
TIME SHEET
| PROJECT NAME |  | Consultancy services related to to Supervision of Engineering Design Supply and Installation of 15kV Switching Substations and Rehabilitation of Associated Distribution of Lines in Kigali
| CONTRACT REF. : |  | 027/03/025/IBC GROUP-CEO/jb
| LOAN No |  | IBC Group PLC
| COUNTRY : |  | Rwanda
| EXPERT : |  | Prince Jean Claude IRANZI
| POSITION : |  | Junior Civil Engineer
| Month: | July | Year: | 2025
| Date | Day of Week | Day worked | Day spent on place of work | Day spent outside of working Place | Place of work | Description of activities (Trip, Mission, Reporting, Making Documents, workshop...)
| 1 | Saturday
| 2 | Sunday
3
4
| 5 | Wednesday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, MINIPLAN, Kanombe Airport | Supervised the final touches on cabin doors and windows at Urugwiro 1, together with drainage and plinth protection finishes. Followed up at Urugwiro 2 where the team was curing the roof slab concrete and progressing with the external plaster works. At MINIPLAN, guided the team on fence wall foundation stone masonry, welding of flat bars, and shuttering along the cable trench wall. Later in the day, moved to Kanombe Airport to oversee rebar work and shuttering for the cabin tie beam.
| 6 | Thursday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, MINIPLAN, Kanombe Airport | At Urugwiro 1, I reviewed finishing progress on cabin doors and windows, ensuring compliance with specifications. At Urugwiro 2, I followed up on roof slab curing and monitored the quality of the external plastering works. At MINIPLAN, I supervised the casting of concrete for the cable trench, checked fabrication works for doors and windows, and verified reinforcement fixing on fence wall columns. At Kanombe Airport, I monitored reinforcement placement and shuttering preparation for the cabin tie beam, ensuring proper alignment and workmanship.
| 7 | Friday | 1 | 1 |  | Kanombe Airport | Supervised the casting of concrete for the cabin tie beam. Verified workmanship and ensured compliance with quality standards during concreting operations.
| 8 | Saturday
| 9 | Sunday
| 10 | Monday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, MINIPLAN, Kanombe Airport | At Urugwiro 1, I checked ongoing painting works inside the cabin and reviewed the drainage and cable trench finishing. At Urugwiro 2, I followed up on external plastering of the cabin, monitored the removal of roof slab shuttering, and inspected the installation of doors and windows. At MINIPLAN, I supervised concrete works for fence wall columns and the ground beam, observed the progress of door and window fabrication, and verified the removal of shuttering along the cable trench. At Kanombe Airport, I monitored backfilling and hardcore filling of the cable trench and assessed blockwork progress on the cabin superstructure up to roof beam level.
| 11 | Tuesday | 1 | 1 |  | Urugwiro 2, MINIPLAN, Kanombe Airport | At Urugwiro 1, I checked drainage and trench finishing around the cabin, ensuring proper alignment and structural safety. At Urugwiro 2, I reviewed plastering works, observed the removal of roof slab shuttering, and monitored installation progress for doors and windows as the structure approached closure stage. At MINIPLAN, I supervised backfilling with compaction along the cable trench and followed up on door and window fabrication to support structural enclosure【uploaded image】. At Kanombe Airport, I oversaw structural preparations, including shuttering works and floor bed stabilization, to maintain quality standards for the upcoming roof beam stage.
| 12 | Wednesday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, MINIPLAN, Kanombe Airport | At Urugwiro 1, I followed up on the completion of drain and cable trench finishing, ensuring proper water management and duct integrity around the cabin. At Urugwiro 2, I checked plastering progress, observed the removal of roof slab shuttering, and reviewed the ongoing installation of doors and windows as the cabin moved closer to finishing stage. At MINIPLAN, I supervised shuttering for fence wall columns, monitored fabrication of doors and windows, and verified backfilling with compaction around the cable trench. At Kanombe Airport, I inspected shuttering preparations for the cabin roof beam and confirmed the placement of quarry dust on the cabin floor bed to improve structural stability
| 13 | Thursday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, MINIPLAN, Kanombe Airport | At Urugwiro 1, I checked drainage and trench finishing around the cabin, ensuring proper alignment and structural safety. At Urugwiro 2, I reviewed plastering works, observed the removal of roof slab shuttering, and monitored installation progress for doors and windows as the structure approached closure stage. At MINIPLAN, I supervised backfilling with compaction along the cable trench and followed up on door and window fabrication to support structural enclosure. At Kanombe Airport, I oversaw structural preparations, including shuttering works and floor bed stabilization, to maintain quality standards for the upcoming roof beam stage.
| 14 | Friday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, MINIPLAN, Kanombe Airport | At Urugwiro 1, I checked final touch works including cabin painting and supervised the start of electrical installations, with wiring and fitting of basic fixtures underway. At Urugwiro 2, I monitored plastering progress on the cabin walls and followed excavation works for the cable trench to ensure alignment and proper depth. At MINIPLAN, I supervised hardcore filling on the cabin floor bed and observed concrete works on fence wall columns, strengthening the site’s structural stability. At Kanombe Airport, I oversaw shuttering preparations for the roof beam and slab while stirrup reinforcement fabrication was carried out to secure the structure before slab casting.
| 15 | Saturday
| 16 | Sunday
| 17 | Monday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, MINIPLAN, Kanombe Airport, Utexrwa, Lue Elephant | At Urugwiro 1, I reviewed cabin wiring works and checked backfilling with compaction in the switchyard, marking a transition toward final service installations. At Urugwiro 2, I followed plastering works inside the cabin and supervised trench excavation for future cable routing. At MINIPLAN, I monitored hardcore filling and quarry dust spreading on cabin floors, and checked fabrication of doors and windows, along with welding activities. At Kanombe Airport, I oversaw shuttering for the roof beam and slab, along with reinforcement placement to support structural elevation. At Utexrwa, I noted completion of basic earthworks, installation of hoarding, and placement of project signage as part of site mobilization. At Lue Elephant, I supervised earthworks to reduce ground level and coordinated relocation of equipment, noting that pending electrical works required a scheduled power outage.
| 18 | Tuesday | 1 |  | 1 | Home | Public holiday. I worked from home, continued typing minutes and organizing project documents.
| 19 | Wednesday | 1 |  | 1 | Home | Public holiday. I worked from home, continued typing minutes and organizing project documents.
| 20 | Thursday | 1 |  | 1 | Home | Public holiday. I worked from home, continued typing minutes and organizing project documents.
| 21 | Friday | 1 |  | 1 | Home | Public holiday. I worked from home, continued typing minutes and organizing project documents.
| 23 | Saturday
| 24 | Sunday
| 25 | Monday | 1 | 1 |  | Utexrwa | Supervised the casting of concrete for the cabin substructure footings and confirmed that curing commenced successfully. Noted site constraints limiting additional manpower due to restricted working space, which may affect productivity. Checked health, safety, and environmental compliance, with PPE observed in use and material handling monitored.
| 26 | Tuesday | 1 | 1 |  | Utexrwa | Supervised shuttering works for cabin substructure columns and confirmed completion of concrete casting. Verified the completion of cable trench excavation, ensuring proper alignment and depth. Observed safe handling and storage of materials, proper use of PPE, and compliance with safety measures throughout the day.
| 26 | Tuesday | 1 | 1 |  | Urugwiro 2 | Supervised plastering works inside the cabin and confirmed completion of cable trench excavation. Verified finishing to the roof slab parapet wall and monitored the start of plinth protection around the cabin. Oversaw concreting of the substructure footings and screed works on the cabin roof slab. Noted that all safety requirements were observed, with proper material handling, organized workspaces, and full compliance with PPE use.
| 27 | Wednesday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, Utexrwa | At MERA, I monitored trench plastering, coping installations, cable trench excavations, site cleaning, and external plinth finishes. At MINIPLAN, I supervised roof slab curing to maintain concrete integrity. At PH APAPE, I oversaw foundation compaction, formwork setups, rebar placements, and concrete casting for the cabin foundation. At Rugwiro 2, I monitored waterline trench excavations and pipe laying alignments. At Rukiri, I reviewed fence footing excavations and backfilling compaction. At Urugwiro 1, I supervised kerbstone laying for the cabin walkway and compaction of paved zones. At Kanombe Airport, I checked generator foundation casting and transformer base preparation.
| 27 | Thursday | 1 | 1 |  | Urugwiro 1, Urugwiro2, MERA, MINIPLAN, PH APAPE Line | Urugwiro 1 — Reviewed final painting to cabin walls and soffit and followed up on soak-pit finishing; site remained orderly and productive. Urugwiro 2 — Supervised a multi-front push: cabin plastering, copper earthing, roof-slab screed, and plinth protection, all carried out to plan. Utexrwa — Monitored trench blinding, shuttering and rebar fixing, base concreting, and stone-masonry foundation works; coordination and logistics were well managed.
| 28 | Friday | 1 | 1 |  | Urugwiro 1, Urugwiro 2, Kanombe Airport | Urugwiro 1 — Reviewed final painting to cabin walls and soffit; progress steady with no issues recorded. Urugwiro 2 — Monitored plastering, blinding concrete to the cable trench, excavation to expose the trench exit, and plinth protection; coordination remained smooth. Kanombe Airport — Verified completion of reinforcement and formwork (roof beam/slab) and checked associated plastering/trench works in readiness for slab activities.
| 30 | Saturday
| 31 | Sunday
|  |  | 1 | 1 |  | Kanombe Airport, Kibagabaga, MINIPLAN, Rue Elephant, Urugwiro 2, UTEXRWA | At Kanombe Airport, I supervised roof beam and slab concrete casting and verified coordination between labor, mixing crew, and material supply; advised early curing and parapet shuttering to keep momentum. At Kibagabaga, I oversaw demolition of the existing building and excavation to prepare the fence wall foundation, with housekeeping and safety maintained throughout. At MINIPLAN, I reviewed cabin plaster finishes and welding of angle irons along cable trench edges; teams coordinated smoothly with site safety in place. At Rue Elephant, I monitored earthworks to reduce ground level and managed constraints caused by live power and telecom cables crossing the plot, coordinating careful maneuvering. At Urugwiro 2, I followed plastering progress, checked shuttering to the cable trench, and monitored plinth protection activities, with steady productivity on all tasks. At UTEXRWA, I supervised shuttering to the plinth beam, rebar fixing, concrete works to the trench base, and stone-masonry foundation activities; supply continuity for steel and cement was emphasized.
|  |  | 1 | 1
| TOTAL of MONTH |  | 21 | 17 | 4
By signing this timesheet, I hereby certify that (i) the activities described reflect the time spent working on this project for the duration indicated, and (ii) that the indicated days worked for this project are not, and will not be, reflected in timesheets for other companies and/or institutions for the same working days.
| Adrien ISHINGIRO |  |  |  |  | 19/8/2025 | Moses ISHINGIRO 2025-08-19
| Civil Engineer | [5 empty] | Resident Engineer
Date and signature of the Client
[9 empty] | Formule Mois | Jour Semaine |  | Mois |  | Valeur de saisie | Année
[9 empty] | 7 | 1 | Monday | April | 4 | 0 | 2021
[10 empty] | 2 | Tuesday | August | 8 | 0.5 | 2022
[10 empty] | 3 | Wednesday | December | 12 | 1 | 2023
[10 empty] | 4 | Thursday | February | 2 |  | 2024
[10 empty] | 5 | Friday | January | 1 |  | 2025
[10 empty] | 6 | Saturday | July | 7
[10 empty] | 7 | Sunday | June | 6
[12 empty] | March | 3
[12 empty] | May | 5
[12 empty] | November | 11
[12 empty] | October | 10
[12 empty] | September | 9
Note on E11: USER: